## 1 · Vision & OKRs
REGULA · GO-TO-MARKET STRATEGIC PLAN
April 2026 – March 2027 · EU AI Act High-Risk Deadline: 2 August 2026
VISION |  | Become the default developer tool for EU AI Act compliance — the first thing a team runs before shipping AI to Europe.
MISSION |  | Give every developer — from solo founder to enterprise team — a free, honest, code-level answer to 'is my AI system high-risk?' in under 60 seconds.
PRODUCT |  | Regula v1.5.0 · Free CLI · PyPI: regula-ai · GitHub: kuzivaai/getregula · getregula.com · MIT licence · Zero dependencies
MARKET CONTEXT (verified, April 2026)
Metric | Data Point | Implication
AI governance market size 2026 | $492M (Gartner Feb 2026) | Growing to $1B+ by 2030
EU AI Act high-risk deadline | 2 August 2026 (Annex III) | Digital Omnibus backstops: 2 Dec 2027 (stand-alone high-risk) / 2 Aug 2028 (embedded in products) — trilogues ongoing. Treat Aug 2026 as working deadline.
Enterprise GRC platforms (OneTrust, IBM) | No published list prices | Regula is free. OneTrust/IBM do not disclose AI governance pricing; analyst reports cite annual contracts well above €10,000.
SME self-assessment cost | €9,500 – €14,500 + internal time | Source: Intellera Consulting (2024). Covers compliance + conformity assessment per high-risk AI system. Regula eliminates the triage phase.
Max penalty (prohibited AI, Art.5) | €35M or 7% global turnover | For prohibited practices only. High-risk AI non-compliance (Art.99): €15M or 3% turnover. Most SMEs face the lower tier.
Top open-source competitor | EuConform — 107 ★ (Apr 2026) | Browser-based, no CLI, no CI/CD integration. Verified via GitHub API, April 2026.
Regula GitHub stars at launch | 0 (repo created 25 Mar 2026) | Honest starting point
Regula PyPI | regula-ai v1.5.0 — live | 748 tests passing, 0 open issues
ANNUAL OKRs · April 2026 – March 2027
# | Objective | Key Result | Target | By | Measure | Status
O1 | Build developer awareness | GitHub stars | 500 | Oct 2026 | gh api repos/kuzivaai/getregula --jq .stargazers_count | Not started
O1 | Build developer awareness | PyPI monthly downloads | 1,000/mo | Oct 2026 | pypistats.org/packages/regula-ai | Not started
O1 | Build developer awareness | HN Show HN front page | 1 post | May 2026 | news.ycombinator.com | Draft ready
O1 | Build developer awareness | DEV.to article published | 1 article | May 2026 | dev.to/@kuzivaai | Not started
O2 | Drive real-world adoption | Unique CLI installs (pip) | 500 | Dec 2026 | PyPI download stats | Not started
O2 | Drive real-world adoption | GitHub issues opened by users | 10 | Oct 2026 | github issues list | Not started
O2 | Drive real-world adoption | Public 'regula check' reports | 5 | Sep 2026 | Link collection | Not started
O3 | Enter compliance ecosystem | Listed on artificialintelligenceact.eu | 1 | Jul 2026 | Manual verification | Not started
O3 | Enter compliance ecosystem | Listed in awesome-claude-code PR merged | 1 | Jun 2026 | github PR | Not started
O3 | Enter compliance ecosystem | IAPP or EU SME Alliance mention | 1 | Aug 2026 | Manual tracking | Not started
O4 | Maintain product quality | Test pass rate | 100% | Ongoing | python3 tests/test_classification.py | 748/748 PASS
O4 | Maintain product quality | PyPI release cadence | 1/quarter | Ongoing | pypi.org/project/regula-ai | v1.5.0 live
O4 | Maintain product quality | False positive rate on real OSS | < 5% | Sep 2026 | Manual evaluation on 3+ repos | Not measured
O5 | Explore sustainability | Enterprise enquiries received | 3 | Mar 2027 | Email / contact form | Not started
O5 | Explore sustainability | Open-source sponsors (GitHub) | 1 | Mar 2027 | github.com/sponsors/kuzivaai | Not started

## 2 · 12-Month Roadmap
12-MONTH MILESTONE ROADMAP · April 2026 – March 2027
Working deadline: 2 Aug 2026 · Omnibus backstops: 2 Dec 2027 (stand-alone) / 2 Aug 2028 (embedded) — trilogues ongoing
Phase | Month | Milestone | Actions Required | Owner | Success Metric | Status | Priority | Notes
Phase 1 Pre-Launch | Apr 2026 | GitHub repo ready for HN | ✓ Description set ✓ Topics set ✓ Release v1.5.0 published ✓ Homepage URL set □ README hero GIF/screenshot □ CONTRIBUTING.md updated | You | Repo looks polished | In progress | P0 | All ✓ items done today
Phase 1 Pre-Launch | Apr 2026 | Landing page verified live | □ Confirm getregula.com serves index.html □ Check robots.txt, sitemap indexed □ Test email capture form end-to-end □ Mobile render check | You | getregula.com loads < 2s | Not started | P0 | Blocker before Show HN
Phase 1 Pre-Launch | Apr 2026 | DEV.to article drafted | □ Title: 'I scanned 5 open-source AI repos for EU AI Act compliance' □ Run regula on LangChain, Hugging Face, PrivateGPT, Ollama, AutoGPT □ Show real output, honest false-positive rate □ Link to GitHub repo | You | Article published on DEV.to | Not started | P1 | Evidence-first marketing
Phase 2 Launch | May 2026 | Show HN submitted | □ Post on Monday or Tuesday morning ET □ Title: Option A or C from SHOW_HN_DRAFT.md □ Link to GitHub repo, not landing page □ Be present for 4+ hours to answer comments □ Answer every technical question honestly | You | Top 30 on HN front page | Not started | P0 | Primary launch channel
Phase 2 Launch | May 2026 | awesome-claude-code PR submitted | □ Find the awesome-claude-code repo □ Regula has Claude Code hooks in hooks/ □ Submit PR with brief description | You | PR merged | Not started | P1 | Niche but highly targeted
Phase 2 Launch | May 2026 | Product Hunt submission | □ Create PH product page with screenshots □ Schedule for Tuesday launch □ Ask 5 users to upvote on launch day | You | Top 10 in dev tools category | Not started | P2 | Second wave after HN
Phase 3 Ecosystem | Jun 2026 | Listed on artificialintelligenceact.eu | □ Contact the site editors □ Submit tool to their tools/resources directory □ Offer to write a guest article on code-level risk detection | You | Listed on site (150K+ users/mo) | Not started | P0 | Highest-ROI channel for this audience
Phase 3 Ecosystem | Jun 2026 | EU Digital SME Alliance outreach | □ Find their tool submission form □ Submit Regula as free SME compliance tool □ Emphasise: free, no account, 60 seconds | You | Listed in SME directory | Not started | P1 | Target audience: SMEs building AI
Phase 3 Ecosystem | Jul 2026 | IAPP outreach | □ Find relevant IAPP community / knowledge base □ Contribute article or tool listing □ Frame as: 'triage tool for DPOs reviewing AI systems' | You | Mention in IAPP resource | Not started | P2 | DPO/compliance officer audience
Phase 3 Ecosystem | Jul 2026 | LinkedIn content series begins | □ 4 posts: 'What the EU AI Act requires from your code' □ 1 post per week, each with a specific Article □ End each with: 'regula check . will flag this in seconds' □ Target: CTOs, DPOs, AI engineers | You | 100+ impressions/post avg | Not started | P2 | Slow burn, builds authority
Phase 4 Deadline | Aug 2026 | EU AI Act enforcement day (Aug 2) | □ Publish blog post: 'The deadline is here. Here's what to check first.' □ Pin to GitHub README □ Share on LinkedIn, HN, DEV.to □ Be available for DMs/emails from developers | You | 500+ GitHub stars by Aug 15 | Not started | P0 | Highest organic traffic window of the year
Phase 4 Deadline | Aug 2026 | Real-world accuracy evaluation published | □ Run regula on 5 public OSS AI repos □ Manually verify findings (no inflation) □ Publish honest precision/recall numbers □ Compare to self-test numbers | You | Published evaluation doc | Not started | P0 | Credibility is the product
Phase 5 Growth | Sep 2026 | Community feedback integration | □ Review all GitHub issues opened by users □ Prioritise false-positive improvements □ Ship v1.6.0 with user-reported fixes □ Thank contributors publicly | You | v1.6.0 released | Not started | P1 | Issues are a success metric
Phase 5 Growth | Oct 2026 | 1,000 PyPI downloads/month milestone | □ Track via pypistats.org weekly □ If behind: revisit Show HN with new angle □ If ahead: write case study post | You | 1,000 downloads/month | Not started | P1 | Lagging indicator of distribution success
Phase 5 Growth | Nov 2026 | r/python and r/programming posts | □ Participate in existing compliance/AI Act threads for 4 weeks first □ Post 'I scanned the top 50 PyPI AI packages for EU AI Act compliance' □ Show real data, link to results gist | You | 200+ upvotes on main post | Not started | P2 | 80/20 rule: participate first
Phase 5 Growth | Dec 2026 | 500 GitHub stars milestone | □ Review star acquisition trajectory □ If behind: identify which channel drove most stars □ Double down on that channel | You | 500 stars | Not started | P1 | Vanity metric but signals discoverability
Phase 6 Sustain | Jan 2027 | GitHub Sponsors page live | □ Enable GitHub Sponsors for kuzivaai org □ Set tiers: $5 (supporter), $25 (team), $100 (company) □ Add sponsor badge to README | You | 1 sponsor | Not started | P2 | Sustainability, not revenue
Phase 6 Sustain | Feb 2027 | Enterprise enquiry pipeline | □ Add 'Enterprise / team support' form to getregula.com □ Define offering: onboarding, custom rules, audit support □ Price range: €500-€2,000/day consulting | You | 3 enquiries received | Not started | P2 | Explore only if open-source traction exists
Phase 6 Sustain | Mar 2027 | Year-1 retrospective | □ Measure all OKRs vs targets □ Write public retrospective post □ Define v2 roadmap based on user feedback | You | Retro published | Not started | P3 | Accountability and direction

## 3 · Distribution Channels
DISTRIBUTION CHANNELS · Ranked by Audience Fit & Effort-to-Impact
Priority | Channel | Audience Fit | Est. Reach | Effort | When | Action | Status
P0 | Show HN (Hacker News) | Developers building AI — exact audience | ~10K–100K unique visits if front page (reported outcomes) | Low (1 post + 4h present) | May 2026 | Post Mon/Tue morning ET. Title: 'Show HN: Regula — scan your AI project for EU AI Act risk in 10 seconds'. Link to GitHub repo. Be honest about precision. | Not started
P0 | artificialintelligenceact.eu | EU AI Act practitioners — highest conversion | 150K+ users/month (self-reported) | Med (outreach + article pitch) | Jun 2026 | Contact site editors. Submit to tools directory. Offer guest article: 'Code-level EU AI Act risk detection — how it works'. | Not started
P0 | DEV.to article | Developers — curious, searchable | 10K–100K reads (SEO + community) | Med (research + write) | May 2026 | Title: 'I scanned 5 open-source AI projects for EU AI Act compliance'. Run regula on LangChain/Ollama/AutoGPT. Show real output. Honest FP rate. | Not started
P1 | EU Digital SME Alliance | SMEs building AI in EU — budget-constrained | Directory listing (unknown visitors) | Low (form submission) | Jun 2026 | Submit via their tool listing form. Emphasise: free, no account, 60 seconds, zero dependencies. | Not started
P1 | awesome-claude-code PR | Claude Code users — overlapping toolchain | Niche but targeted | Low (1 PR) | May 2026 | Submit PR. Regula has Claude Code hooks. Mention: regula-ignore works in AI-generated code. | Not started
P1 | GitHub Topics (#eu-ai-act) | Devs searching compliance tools on GitHub | Organic search traffic | Done (topics set) | Done | Topics already set: eu-ai-act, compliance, ai-safety, static-analysis, python, cli. | Done
P1 | PyPI discoverability | Python developers installing AI tools | PyPI search + pip install | Low (keywords in pyproject.toml) | Apr 2026 | Add classifiers to pyproject.toml: 'Topic :: Security', 'Topic :: Software Development :: Quality Assurance'. Verify description renders on PyPI. | Not started
P1 | r/python + r/programming | Python/developer community | 5K–50K views if popular | High (participate first, 4 weeks) | Nov 2026 | 80/20 rule: participate in EU AI Act threads for 4 weeks. Then post: 'I scanned the top 50 PyPI AI packages for EU AI Act compliance — here's what I found'. | Not started
P2 | LinkedIn content series | CTOs, DPOs, AI engineers | 100–1,000 per post (cold start) | Med (4 posts/month) | Jul 2026 | 4-post series: 'What the EU AI Act actually requires from your code, article by article'. Each post ends with a 'regula check .' call to action. | Not started
P2 | Product Hunt | Broad tech audience — less targeted | 500–5,000 if top 10 | Med (prep + launch day) | Jun 2026 | Second wave after HN. Create product page. Screenshots of CLI output. Schedule Tuesday launch. | Not started
P2 | IAPP community | Privacy/compliance professionals | Unknown — conservative audience | High (community membership first) | Jul 2026 | Attend IAPP forums. Contribute to AI Act compliance matrix discussion. Frame Regula as triage tool for DPOs, not a replacement for legal review. | Not started
P2 | MCP server directories | Claude/Cursor users | Niche and growing | Low (listing submission) | May 2026 | List the Regula MCP server in Claude/Cursor tool directories. Good for developer mindshare. | Not started
P3 | AI Act Service Desk (EC) | EU startups/SMEs seeking tools | Low visibility — uncertain | Low | Aug 2026 | Submit around the August deadline when traffic to official resources peaks. | Not started
P3 | YouTube tutorial | Visual learners, international reach | Long-tail SEO value | High (record, edit, upload) | Sep 2026 | 5-minute tutorial: 'Run regula check on your AI project'. Show prohibited → high-risk → compliant flow. Real code, real output. | Not started

## 4 · Competitive Landscape
COMPETITIVE LANDSCAPE · Verified Data, April 2026
All star counts verified via GitHub API. All claims verified against public sources.
Tool | Stars (verified) | Type | Approach | CLI? | CI/CD? | Languages | Regula Advantage | Risk to Regula
Regula (ours) | 0 ★ | CLI / code scanner | Regex + AST + tree-sitter. 33 commands, 32 named pattern groups, 11 frameworks, 8 languages. Generates Annex IV docs, evidence packs, remediation plans. | Yes | Yes (action.yml) | 8 (Py/JS/TS/Java/Go/Rust/C/C++) | Most commands (33), most languages (8), only tool with Annex IV doc generation + evidence pack + gap scoring. Free. | Starting from 0. Late entrant. Systima overlaps on CLI+CI/CD.
EuConform | 107 ★ (Apr 2026) | Browser app | Risk classification (Art.6/7) + bias eval (CrowS-Pairs). Offline-first, no cloud. PDF reports. | No | No | N/A (form-based) | No CLI, no CI/CD. Cannot integrate into a dev workflow. No codebase scanning. | 107 stars as of Apr 2026 — strong first-mover advantage in OSS space
Systima Comply | 0 ★ | CLI / GitHub Action | npm package + GitHub Action + TypeScript API. Scans codebase for EU AI Act risks. Domain-based severity. PDF reports. Call-chain tracing. | Yes | Yes (GH Action) | TS-native; also scans Py/Go/Java/Rust via tree-sitter | Regula covers 8 languages with dedicated patterns; Systima is TypeScript-native. Regula has 33 commands and generates Annex IV docs. | Direct competitor — CLI + CI/CD + codebase scanning. Created 14 Mar 2026.
AgentGuard | 10 ★ | Runtime middleware | 3-line Python import. Wraps LLM agents. Runtime policy enforcement, not code scanning. | No | Yes (SDK) | Python (middleware) | Different use case: runtime vs scan-time. Complementary, not competitive. | Could expand to code scanning
EU AI Radar | ? | Static web tool | 5-question quiz. Maps to risk band. No code scanning. | No | No | N/A | Trivial tool. Different depth entirely. | Very low — different depth
mcp-eu-ai-act | 2 ★ | MCP server | ArkForge MCP scanner. Detects EU AI Act violations via MCP protocol. | Via MCP | Via MCP | MCP-compatible | Very early. Our MCP server is a distribution channel, not a competitor. | Could gain traction with Claude/Cursor users before us
G0 (AgentBouncr) | ? | Agent control layer | Scan, test, monitor for AI agents. LangChain/CrewAI/AutoGen/RAG. HMAC audit chains. ConsentGate. | No | Yes | Python | Agent-focused vs code-focused. Different buyer. | Could expand to code scanning
KLA Digital | N/A | SaaS platform | AI governance SaaS. Cross-framework mapping. Pricing on request — no public list prices (Apr 2026). | No | No | Platform | We're free. They target enterprise compliance officers, not developers. | Credibility: established brand vs unknown
EuroComply | N/A | SaaS — SME-focused | EU AI Act + NIS2 + GDPR + CRA + Data Act in one platform. Browser-based. | No | No | Platform | Targets same SME audience. Broader regulation coverage. No code scanning. | Most direct SaaS overlap with Regula's audience
compl-ai | ? | OSS eval framework | Open-source compliance-centred evaluation for generative AI. compl-ai.org. Research-grade. | No | Partial | Python | Research-focused, not developer-focused. Different use case. | Could grow into developer tool territory
HONEST ASSESSMENT
Regula has the broadest feature set in the open-source space (33 commands, 8 languages, 11 frameworks, 32 named pattern groups, Annex IV doc generation). One direct CLI+CI/CD competitor exists: Systima Comply (TypeScript-native, also scans Py/Go/Java/Rust via tree-sitter, created 14 Mar 2026, 0 stars). Regula's advantage over Systima is pattern depth (32 named groups vs scanner heuristics) and command breadth (33 commands vs scan-only). EuConform leads on OSS mindshare (107 stars, Apr 2026). The honest risk: EuConform has 107 stars and 4 months head start. Systima is a newer but direct competitor. Distribution — not product quality — is the critical path. Every week without a Show HN post or distribution action is a week competitors compound their lead. The window is August 2026. After the deadline passes, urgency drops and the market fragments further.

## 5 · OKR Tracker
QUARTERLY OKR TRACKER · Update Weekly
Q1 Apr–Jun 2026 · Theme: Pre-launch & launch
Key Result | Baseline | Target | Week 1 | Week 2 | Week 3 | Week 4 | RAG Status
GitHub stars | 0 | 50 |  |  |  |  | R / A / G
PyPI downloads (total) | 0 | 200 |  |  |  |  | R / A / G
Show HN submitted | No | Yes |  |  |  |  | R / A / G
DEV.to article published | No | Yes |  |  |  |  | R / A / G
Landing page verified live | No | Yes |  |  |  |  | R / A / G
awesome-claude-code PR | No | Yes |  |  |  |  | R / A / G
Q2 Jul–Sep 2026 · Theme: Ecosystem & deadline window
Key Result | Baseline | Target | Week 1 | Week 2 | Week 3 | Week 4 | RAG Status
GitHub stars | ? | 200 |  |  |  |  | R / A / G
PyPI monthly downloads | ? | 500 |  |  |  |  | R / A / G
artificialintelligenceact.eu listed | No | Yes |  |  |  |  | R / A / G
LinkedIn posts published | 0 | 4 |  |  |  |  | R / A / G
Real-world eval published | No | Yes |  |  |  |  | R / A / G
Aug 2 blog post live | No | Yes |  |  |  |  | R / A / G
Q3 Oct–Dec 2026 · Theme: Growth & community
Key Result | Baseline | Target | Week 1 | Week 2 | Week 3 | Week 4 | RAG Status
GitHub stars | ? | 500 |  |  |  |  | R / A / G
PyPI monthly downloads | ? | 1,000 |  |  |  |  | R / A / G
User-filed GitHub issues | 0 | 10 |  |  |  |  | R / A / G
v1.6.0 shipped | No | Yes |  |  |  |  | R / A / G
r/python post submitted | No | Yes |  |  |  |  | R / A / G
False positive rate (OSS) | N/A | < 5% |  |  |  |  | R / A / G
Q4 Jan–Mar 2027 · Theme: Sustainability & v2 planning
Key Result | Baseline | Target | Week 1 | Week 2 | Week 3 | Week 4 | RAG Status
GitHub stars | ? | 800 |  |  |  |  | R / A / G
PyPI monthly downloads | ? | 2,000 |  |  |  |  | R / A / G
GitHub Sponsors live | No | Yes |  |  |  |  | R / A / G
Enterprise enquiries | 0 | 3 |  |  |  |  | R / A / G
Year-1 retro published | No | Yes |  |  |  |  | R / A / G
v2.0 roadmap defined | No | Yes |  |  |  |  | R / A / G
HOW TO USE THIS TRACKER
• Update the Week columns each Friday. Enter actual numbers, not estimates.
• RAG = Red (off track, needs action) / Amber (at risk, monitor) / Green (on track).
• A metric that stays Red for 2+ weeks needs a plan change, not a colour change.
• Baseline = value at start of quarter. Target = realistic stretch, based on market data above.
• Do not update baselines mid-quarter — that hides regression.

## 6 · First 8 Weeks
FIRST 8 WEEKS — SPRINT PLAN · April 3 – May 29, 2026
These 8 weeks determine whether the Show HN lands before or after the August deadline crowd
Week | Dates | Focus | Must-Do Tasks | Done? | Notes
Wk 1 | Apr 3–9 | Pre-launch: repo & landing | □ Verify getregula.com is live and loads correctly □ Test email capture form end-to-end □ Add README hero screenshot or GIF of 'regula check' output □ Add PyPI classifiers to pyproject.toml (Topic :: Security etc.) □ Verify PyPI page renders description correctly | □ Not done | Blocking: landing page must be verified before HN
Wk 2 | Apr 10–16 | Pre-launch: DEV.to research | □ Run 'regula check .' on LangChain (pip install langchain) □ Run on Ollama Python client □ Run on PrivateGPT or similar □ Document findings honestly (what it caught, what it missed) □ Draft DEV.to article outline | □ Not done | Need 3-5 real repos with honest output before publishing
Wk 3 | Apr 17–23 | DEV.to article: write & publish | □ Write full article: 'I scanned 5 open-source AI repos for EU AI Act compliance' □ Include real terminal output (screenshots or code blocks) □ Be honest about false positives □ Publish on DEV.to □ Share on LinkedIn | □ Not done | Article is evidence. Show the tool working, not just describe it.
Wk 4 | Apr 24–30 | Show HN prep | □ Read 10 recent successful Show HN posts — note what made them land □ Finalise HN post title (from SHOW_HN_DRAFT.md) □ Prepare answers to all 6 predictable questions in draft □ Choose a Tuesday or Wednesday morning to post □ Block 4 hours in calendar for that day | □ Not done | Timing matters. Clear your calendar for launch day.
Wk 5 | May 1–7 | Show HN LAUNCH | □ POST Show HN on chosen day, 8–10am ET □ Be present for minimum 4 hours □ Answer every technical question honestly and promptly □ Do NOT be defensive about false positives — acknowledge them □ Thank people who try it and report results | □ Not done | This is the most important week. Clear everything else.
Wk 6 | May 8–14 | Post-HN: follow-up & ecosystem | □ Review all HN comments for product feedback □ Submit to awesome-claude-code □ Submit to MCP server directories □ Respond to any emails/issues from HN traffic □ Note which questions came up most — update FAQ | □ Not done | HN traffic is short-lived. Act on feedback immediately.
Wk 7 | May 15–21 | Product Hunt prep | □ Create PH product page □ Write tagline and description □ Take clean screenshots of CLI output □ Line up 5 people to upvote on launch day □ Schedule for Tuesday launch | □ Not done | PH is second wave — don't launch same week as HN
Wk 8 | May 22–29 | EU ecosystem outreach begins | □ Contact artificialintelligenceact.eu editors □ Submit to EU Digital SME Alliance directory □ Write first LinkedIn post in the 4-post series □ Review PyPI download stats — set Q2 baseline □ Review GitHub stars — assess HN impact honestly | □ Not done | If HN didn't land: diagnose why before next attempt